RAH-E-RAVAAN

End-to-End Software Development Plan

A Sprint-Based Delivery Roadmap for an AI-Powered Travel Planning & Tourism Assistance Platform

Final Year Project · BSCS · Artificial Intelligence & Software Engineering

Floated by: Maajid Maqbool

Prepared to accompany the approved UX Design Plan and UX Wireframe Document

July 2026

# Table of Contents

# 1. Introduction & Purpose

This document translates the Rah-e-Ravaan UX Design Plan and UX Wireframe Document into an actionable, end-to-end engineering roadmap. It is organized as a sequence of sprints so the team can plan, build, test, and demo incrementally rather than attempting a single large delivery at the end of the project.

The plan assumes an FYP timeline split across two semesters, with a mid-project evaluation (FYP-I) roughly at the halfway point and a final evaluation (FYP-II) at the end. Sprint numbering, week estimates, and team-size assumptions are stated explicitly wherever used, so they can be scaled up or down to match the team's actual size and calendar.

Scope covered by this plan:

- Customer portal — web (React) and mobile (Flutter), including the AI conversational planner, discovery, itinerary management, bookings, and offline/GPS features.

- Organizer portal — web-only, covering itinerary publishing, participant management, and group GPS tracking, for both travel agencies and institutional trip committees.

- Admin console — web-only, covering organizer approvals, the institution domain registry, moderation, payments oversight, and system configuration.

- The AI/RAG subsystem, the store-and-forward GPS pipeline, and the domain-locked institutional enrollment mechanism, which cut across all three portals.

# 2. Development Methodology & Engineering Practices

## 2.1 Agile/Scrum Framework

The project runs on two-week sprints (Sprint 0 is a one-week setup sprint). Each sprint includes:

- Sprint planning — select backlog items, confirm the Definition of Ready is met, agree on the sprint goal.

- Daily standups (async or synchronous, 15 minutes) — progress, blockers, plan for the day.

- Sprint review/demo — working software demonstrated at the end of every sprint, not just at FYP-I/FYP-II.

- Sprint retrospective — what worked, what didn't, one concrete process change to try next sprint.

## 2.2 Assumed Team Structure

This plan assumes a team of 3–4 students with cross-functional but weighted ownership, which is typical for an FYP of this scope. Adjust sprint pacing proportionally if the team size differs.

- Backend / AI engineer(s) — FastAPI services, RAG pipeline, LangChain orchestration, database design.

- Web frontend engineer — React/Vite/Tailwind, Mapbox integration, customer + organizer + admin web UIs.

- Mobile engineer — Flutter app, offline-first architecture, background GPS/location services.

- Shared responsibility — every member participates in code review, testing, and DevOps; there is no single “QA person” silo.

## 2.3 Version Control & Branching Strategy

- Trunk-based development: `main` is always deployable and protected — no direct pushes.

- Short-lived feature branches named `feature/<sprint>-<short-description>` (e.g. `feature/s5-ai-planner-chat`), merged via pull request within 2–3 days of being opened.

- Every PR requires at least one peer review and a green CI run before merge.

- Commit messages follow Conventional Commits (`feat:`, `fix:`, `chore:`, `test:`, `docs:`) to keep the history and changelog machine-readable.

- Squash-merge to keep `main` history linear and readable.

## 2.4 Definition of Ready / Definition of Done

A backlog item is not pulled into a sprint unless it meets the Definition of Ready:

- User story is written with a clear acceptance criteria list.

- Dependencies (API contracts, design assets, third-party keys) are identified and available.

- The item is estimated and small enough to fit within one sprint.

Every backlog item must meet the baseline Definition of Done before it is considered complete (sprint-specific additions are listed per sprint below):

- Code merged to main via a reviewed PR with passing CI.

- Automated tests written for new logic (unit, and integration where applicable).

- No new critical/high linter or security-scanner warnings introduced.

- User-facing changes verified against the relevant wireframe screen.

- Documentation (README, API spec, or ADR) updated if behavior or contracts changed.

## 2.5 CI/CD Pipeline

- On every pull request: lint, static type checks, and the unit/integration test suite run automatically via GitHub Actions.

- On merge to `main`: build Docker images, run the full test suite, and auto-deploy to a staging environment.

- Production deploys require a manual approval gate after staging smoke tests pass.

- Mobile: a separate CI job builds Android/iOS artifacts and runs Flutter widget tests on every PR touching the mobile app.

- Secrets and API keys are never committed; they are managed via environment variables and the CI provider's secret store.

## 2.6 Testing Strategy

Testing follows a pyramid shape — many fast unit tests, fewer integration tests, and a small but critical set of end-to-end tests covering the five key user flows named in the UX plan.

- Unit tests: backend services (Pytest), aiming for ≥70% coverage on business logic; Flutter widget/unit tests for core screens.

- Integration tests: API contract tests against a real Postgres/Redis/Qdrant test instance (via Docker Compose in CI).

- End-to-end tests: Playwright/Cypress for web, covering AI trip planning, institutional enrollment, organizer publishing, admin approval, and parent tracking (built out fully in Sprint 15, but critical-path smoke tests exist from Sprint 5 onward).

- Manual QA checklist run each sprint review against the sprint's own acceptance criteria before the demo.

- Security and load testing pass in Sprint 15, ahead of production deployment.

## 2.7 Documentation Standards

- OpenAPI/Swagger spec generated directly from the FastAPI backend and kept in sync automatically.

- Architecture Decision Records (ADRs) for any decision with long-term consequences (e.g. choice of vector DB, GPS sync protocol).

- A README per service/app covering local setup, environment variables, and how to run tests.

- A living Postman/Insomnia collection alongside the OpenAPI spec for manual API exploration.

## 2.8 Environment Strategy

- Local — Docker Compose running Postgres, Redis, Qdrant, and the backend for each developer.

- Staging — mirrors production configuration on Railway/Render (backend) and Vercel (web); auto-deployed from `main`.

- Production — separate managed database/cache/vector-store tiers, deployed only via the manual-approval pipeline gate.

# 3. System Architecture Snapshot

A brief snapshot of the target architecture, established in Sprint 0 and evolved incrementally through the sprints below. Full architectural detail belongs in the ADRs and the final documentation (Sprint 16), not in this plan.

## 3.1 Client Applications

- Web app — React + Vite + Tailwind CSS, serving the customer, organizer, and admin portals from one codebase with role-based routing.

- Mobile app — Flutter, customer portal only, with SQLite for offline storage and platform background-location services for GPS logging.

## 3.2 Backend Services

- A modular FastAPI backend organized around bounded contexts: auth, itinerary/AI-planner, organizer, admin, payments, and GPS/tracking — deployed as a single service initially, with clear internal module boundaries that allow splitting into separate services later if needed.

- REST endpoints for CRUD-style operations; WebSockets/SSE for the AI planner chat stream and real-time GPS/notification updates.

## 3.3 Data Layer

- PostgreSQL — system of record for users, trips, itineraries, enrollments, bookings, and payments.

- Redis — session/cache layer, rate limiting, and pub/sub for real-time notifications.

- Qdrant — vector store for destination and itinerary embeddings powering RAG retrieval.

## 3.4 AI/ML Subsystem

- OpenAI API for generation, Sentence Transformers for embeddings, LangChain for agent orchestration and retrieval-augmented prompting.

# 4. Timeline Overview & Milestone Mapping

The roadmap below groups the 17 sprints (Sprint 0 through Sprint 16) into six delivery phases across an assumed ~33-week, two-semester FYP calendar.

| Phase | Sprints | Duration | Key Milestone |
| --- | --- | --- | --- |
| 1. Foundation | Sprint 0–2 | Weeks 1–5 | Working dev environment, auth, design system |
| 2. Core Customer Experience | Sprint 3–6 | Weeks 6–13 | AI planner, discovery, itinerary management live on web |
| 3. Organizer & Institutional Flows | Sprint 7–8 | Weeks 14–17 | FYP-I evaluation & demo (end of Sprint 7) |
| 4. Admin Console & Mobile Foundation | Sprint 9–10 | Weeks 18–21 | Admin console MVP; Flutter app alpha |
| 5. Offline, GPS & Payments | Sprint 11–13 | Weeks 22–27 | Offline-first mobile, store-and-forward GPS, payments live |
| 6. Hardening & Launch | Sprint 14–16 | Weeks 28–33 | FYP-II final evaluation, production launch |

# 5. Sprint-by-Sprint Development Plan

Every sprint below references the corresponding wireframe screens and UX plan sections so the backlog stays traceable to what was actually designed, rather than generic assumptions.

## Sprint 0 — Project Inception & Environment Setup

Week 1 (1 week)

Sprint Goal:  Stand up the technical foundation and team workflow before any feature work begins.

Key User Stories / Backlog Items

- Initialize repositories: web (React + Vite + Tailwind), mobile (Flutter), backend (Python/FastAPI) with a shared conventions document.

- Docker Compose environment: PostgreSQL, Redis, Qdrant, FastAPI, and web dev server running locally with one command.

- GitHub repo setup: branch protection on main, PR template, issue templates, CODEOWNERS.

- GitHub Actions CI skeleton: lint + test job triggered on every PR (even before real tests exist).

- Provision third-party accounts/keys: Mapbox, OpenAI, Qdrant Cloud (or self-hosted), Safepay/JazzCash sandbox.

- Coding standards configured: ESLint + Prettier (web), flutter_lints + dart format (mobile), Ruff + Black + mypy (backend).

- Draft entity-relationship diagram: users, roles, institutions, domains, trips, itineraries, itinerary_days, enrollments, organizers, payments, gps_logs.

- Set up the product backlog (GitHub Projects/Jira) seeded with epics derived from the UX plan sections 3–5.

Deliverables

- `docker-compose up` brings up the full local stack.

- CI pipeline green on an empty scaffold (proves the pipeline itself works).

- Database schema v1 + ER diagram, reviewed and merged.

- ADR-001: architecture & tooling decisions recorded.

Definition of Done:  Any teammate can clone the repo and run the full stack locally within 15 minutes, following only the README.

Testing Focus:  No feature tests yet — validate that CI fails on a deliberately broken lint rule (pipeline sanity check).

## Sprint 1 — Authentication, RBAC & Domain Foundations

Weeks 2–3

Sprint Goal:  Implement multi-role authentication for Customer, Organizer, and Admin, including institutional email detection.

Key User Stories / Backlog Items

- Customer sign-up: name/email/password + Google OAuth (maps to “Customer sign-up (mobile)” wireframe).

- Institutional email domain detection at signup, surfacing the “institutional email detected” note.

- Organizer registration: Travel Agency vs. Institutional Committee paths, document upload, pending-review state (maps to “Organizer registration (web)” wireframe).

- Admin login: email/password only, mandatory TOTP 2FA, 30-minute inactivity session timeout.

- JWT access/refresh token issuance, RBAC middleware enforced on every route from day one.

- Domain registry table + email-domain matching service (data model only — admin UI arrives in Sprint 8).

Deliverables

- `/auth/*` endpoints (signup, login, refresh, logout, 2FA enroll/verify).

- Postman/Insomnia collection covering all three sign-up paths.

- Basic web sign-up/sign-in screens wired to the API.

Definition of Done:  ≥80% unit test coverage on the auth module; passwords hashed with bcrypt/argon2; token TTLs and refresh rotation documented and reviewed.

Testing Focus:  Unit tests for password hashing, token expiry/refresh, and domain-matching logic; manual test of 2FA enrollment.

## Sprint 2 — Design System, Onboarding & Web Shell

Weeks 4–5

Sprint Goal:  Build a reusable component library and the onboarding experience shared across portals.

Key User Stories / Backlog Items

- Onboarding quiz (travel style, budget range, preferred regions) — 4-step flow matching the wireframe.

- Shared design tokens (maroon/lime brand palette, spacing, radii) implemented as Tailwind config.

- Component library: buttons, cards, form fields, chat bubbles, status badges, nav shells for all three portals.

- Destinations table + basic CRUD API, seeded with an initial Pakistan destination dataset.

- Personalized home/discovery feed skeleton (web): AI prompt hero, trending destinations, group trips section.

Deliverables

- Style guide (Storybook or MDX doc) covering every shared component.

- Functional onboarding quiz and home feed on web.

- `/destinations` CRUD API with seed data.

Definition of Done:  All components documented with props; responsive at 360px+ widths; base color-contrast checked against WCAG AA.

Testing Focus:  Component snapshot/unit tests; manual responsive check at 360px, 768px, 1280px breakpoints.

## Sprint 3 — Destination Discovery Engine

Weeks 6–7

Sprint Goal:  Let users search and browse destinations independently of the AI planner.

Key User Stories / Backlog Items

- Search bar with autocomplete (city, region, landmark).

- Filter panel: province, budget range, activity type, season, accessibility.

- Map view mode — Mapbox-powered interactive map with clustered pins.

- Destination detail page: photo gallery, description, nearby hotels, reviews, weather widget stub, offline-map-patch placeholder.

Deliverables

- `/destinations/search` API with combined filters (indexed via Postgres trigram/full-text search).

- Mapbox integration on web with clustering.

- Destination detail page (web).

Definition of Done:  Search API returns p95 < 300ms on the seeded dataset; e2e test covers search → filter → detail page.

Testing Focus:  API integration tests per filter combination; Playwright e2e for the full discovery flow.

## Sprint 4 — RAG Knowledge Base & Vector Pipeline

Weeks 8–9

Sprint Goal:  Build the retrieval backbone that the AI planner will consume, ahead of the chat UI itself.

Key User Stories / Backlog Items

- Generate destination embeddings (Sentence Transformers) and ingest into Qdrant collections.

- RAG retrieval service: LangChain retriever with reranking over destination + itinerary knowledge.

- Prompt templates for itinerary generation stored as versioned config (admin-editable later, Sprint 9).

- Cost-estimator data pipeline: aggregated transport/hotel pricing dataset with a scheduled refresh job.

Deliverables

- Idempotent embedding-ingestion script with a documented re-run procedure.

- Internal `/rag/retrieve` endpoint.

- Retrieval evaluation harness (a fixed set of sample queries with relevance scoring).

Definition of Done:  Retrieval precision spot-checked against 20 curated queries and signed off by the team; ingestion job is safely re-runnable without duplicating vectors.

Testing Focus:  Retrieval relevance evaluation harness; unit tests on the pricing pipeline's aggregation logic.

## Sprint 5 — AI Conversational Trip Planner (Web)

Weeks 10–11

Sprint Goal:  Ship the platform's core differentiator: a chat-based itinerary generator.

Key User Stories / Backlog Items

- Split-panel planner UI: chat on the left, live itinerary preview on the right (maps to “Customer web — AI planner (split panel)”).

- LangChain agent orchestration: conversation → RAG retrieval → GPT itinerary JSON → rendered day-by-day plan.

- Inline, continuously-updating budget estimator.

- Partial re-generation on edits (e.g. “skip the hike on day 3”) instead of restarting the whole itinerary.

- English + Urdu input handling in the chat.

- Shareable itinerary link generated after user confirmation.

Deliverables

- `/planner/chat` streaming endpoint (SSE or WebSocket).

- Versioned itinerary JSON schema (Pydantic-validated).

- Functional end-to-end web planner.

Definition of Done:  Manual QA script covering 10 representative conversations passes; time-to-first-token budget (<4s) validated under normal load.

Testing Focus:  Contract tests on the itinerary JSON schema; scripted conversation regression suite; latency benchmarking.

## Sprint 6 — Itinerary Management & Collaboration

Weeks 12–13

Sprint Goal:  Let users manage, revisit, and collaboratively edit their trips.

Key User Stories / Backlog Items

- “My Trips” tab with Upcoming / Active / Past filters and per-trip status.

- Trip detail view: day-by-day timeline, map route, cost breakdown, AI-generated packing checklist.

- Collaborative mode: invite companions via link or email; companions can view and suggest edits.

- PDF export of the full itinerary for offline reference.

Deliverables

- `/trips` CRUD + sharing/invite service.

- Companion permission model (owner vs. collaborator).

- Server-side PDF generation (WeasyPrint/ReportLab).

Definition of Done:  Concurrent-edit scenarios tested (two collaborators editing the same day); exported PDFs visually verified against the on-screen itinerary.

Testing Focus:  Integration tests for invite/accept flow and permission boundaries; visual regression check on PDF output.

## Sprint 7 — Organizer Portal Core + FYP-I Demo Prep

Weeks 14–15

Sprint Goal:  Stand up the organizer-facing dashboard and itinerary builder; prepare the FYP-I evaluation demo.

Key User Stories / Backlog Items

- Organizer dashboard: summary stat cards (itineraries published, enrollments, active trips, rating) and recent-activity feed.

- Itinerary builder: day-by-day stop editor with auto-plotted map, visibility settings (Public / Institution-only / Draft), pricing, and an AI-assist pre-fill button powered by RAG.

- Participant management table: enrollment list with domain-verified and GPS-consent columns, approve/reject, CSV export.

Deliverables

- `/organizer/*` endpoints and the organizer web app slice.

- Seeded demo dataset (sample institutional and agency trips).

- FYP-I demo script and supporting slides.

Definition of Done:  Role-based route guarding verified (a customer account cannot reach `/organizer/*`); the full demo runs unattended in the staging environment.

Testing Focus:  RBAC boundary tests across all three roles; staging smoke test rehearsal ahead of the demo.

▶ FYP-I MILESTONE: Mid-project evaluation and demo of the customer + organizer core (AI planner, discovery, itinerary management, organizer publishing).

## Sprint 8 — Institutional Domain Locking & Admin Approvals

Weeks 16–17

Sprint Goal:  Enforce domain-based enrollment locking and stand up the admin approval workflow that governs it.

Key User Stories / Backlog Items

- Admin organizer-approval queue: approve + set domain, reject, or view documents (maps to “Admin — organizer approval queue”).

- Domain registry screen: add institution, view domain/type/organizer/students-verified/status (maps to “Admin — institution domain registry”).

- Enrollment-time domain re-check: a non-matching email is blocked even with a direct link to the itinerary.

- Templated auto-emails on organizer approval/rejection decisions.

Deliverables

- `/admin/organizers` and `/admin/domains` endpoints.

- Transactional email service integration.

Definition of Done:  A spoofed-domain enrollment attempt is provably blocked in an automated test; every admin decision writes an audit-log entry.

Testing Focus:  Security-style test: attempt enrollment with a non-institutional email against a domain-locked trip and assert rejection.

## Sprint 9 — Admin Console Core & Content Moderation

Weeks 18–19

Sprint Goal:  Round out platform-operations tooling for the internal team.

Key User Stories / Backlog Items

- Admin dashboard: platform-wide metrics, revenue summary, and alerts (pending approvals, flagged content, failed payments).

- User management and content moderation: review flagged itineraries/reviews/photos, bulk takedown, a three-strikes warning system with auto-suspend.

- Destination & content management: CRUD for destinations, travel-advisory banner publishing.

- System configuration: feature flags, AI prompt/RAG config editor, notification template editor, audit-log viewer.

Deliverables

- Admin console MVP covering all sections above.

Definition of Done:  Every admin mutation is written to the audit log; admin-only routes verified inaccessible to other roles; a feature-flag toggle is validated live in staging.

Testing Focus:  RBAC tests for admin routes; audit-log completeness test across every mutating admin action.

## Sprint 10 — Mobile App Foundation (Flutter)

Weeks 20–21

Sprint Goal:  Stand up the Flutter customer app on top of the existing backend APIs.

Key User Stories / Backlog Items

- App shell and bottom navigation: Home / Explore / Plan / Trips / Profile.

- Auth screens (sign-up, onboarding quiz) at parity with web.

- Home/discovery feed and destination browse & detail, adapted for mobile.

- Full-screen AI chat planner (mobile variant of the web split-panel).

Deliverables

- Flutter alpha build for Android and iOS.

- Shared typed API client generated from the OpenAPI spec.

- Mobile CI pipeline (build + widget tests) in GitHub Actions.

Definition of Done:  App runs on a physical or emulated device for both platforms; widget tests cover the five core screens.

Testing Focus:  Flutter widget tests; manual device testing on at least one low-end Android device to validate performance assumptions.

## Sprint 11 — Offline-First Architecture & Sync

Weeks 22–23

Sprint Goal:  Implement the offline-first mobile experience the platform is built around.

Key User Stories / Backlog Items

- SQLite local store for itinerary data, cached destination info, and downloaded map tiles.

- “Download itinerary & maps before travel” flow, with an offline indicator in the app header when disconnected.

- Background sync service that runs on reconnect: trip status updates, photo uploads, visited-place logs.

- “Last synced” timestamp shown on all cached content.

Deliverables

- Offline data layer + background sync service; conflict-resolution policy documented.

Definition of Done:  Airplane-mode test suite passes (itinerary and maps remain viewable offline); reconnect sync loses zero data across a scripted scenario.

Testing Focus:  Automated airplane-mode integration test; manual reconnect test with simulated network flapping.

## Sprint 12 — Store-and-Forward GPS Tracking

Weeks 24–25

Sprint Goal:  Ship the safety-tracking pipeline for both the traveler/parent view and the organizer group view.

Key User Stories / Backlog Items

- Background location service logging GPS every 30s (configurable) to local SQLite: timestamp, lat, long, altitude, accuracy, battery.

- Battery-aware interval scaling (auto-switch to 120s below 20% battery).

- Incremental sync — only `synced=false` rows are uploaded; server stitches them into a continuous breadcrumb trail.

- Customer “Live tracking” screen: offline-logging badge, last-synced time, log-entry/battery/interval stats (maps to wireframe).

- Consent-gated parent invite flow with a read-only breadcrumb view (web + mobile).

- Organizer group GPS dashboard: live map plus offline participant cards and a configurable signal-loss alert threshold (maps to “Organizer — group GPS tracking”).

- Missed check-in push notifications to linked parents/organizers.

- Scheduled retention job: GPS logs deleted 30 days after trip end, per the privacy policy.

Deliverables

- GPS logging SDK (Flutter) and `/gps/sync`, `/gps/trips/{id}/breadcrumbs` endpoints.

- Retention cron job with logging/alerting on failure.

Definition of Done:  A simulated 2-hour no-signal scenario reconstructs an accurate breadcrumb trail on reconnect; consent cannot be bypassed (parents cannot self-add); retention job verified end-to-end in staging.

Testing Focus:  Field-simulated offline GPS test; consent-bypass negative test; retention-job dry run against seeded old records.

## Sprint 13 — Bookings & Payments

Weeks 26–27

Sprint Goal:  Integrate accommodation/transport booking and Pakistani payment gateways.

Key User Stories / Backlog Items

- Accommodation search filtered by itinerary dates/location; transport option aggregation (bus/van/flight price estimates).

- Payment integration: Safepay (primary), JazzCash, Raast/PayFast.

- Booking confirmation via email + SMS; cancellation and refund status tracked in-app.

- Organizer analytics: revenue dashboard, payout history (agency accounts).

- Admin payments & financials: transaction log, dispute management, platform-fee configuration, payout scheduling, gateway health status.

Deliverables

- `/bookings` and `/payments` endpoints with gateway webhook handlers, tested against sandbox accounts.

Definition of Done:  Payment webhooks are verified idempotent; a full refund flow is tested end-to-end in sandbox; no raw card/account data is ever persisted (gateway tokens only).

Testing Focus:  Sandbox payment integration tests (success, failure, timeout, duplicate-webhook scenarios); webhook signature verification tests.

## Sprint 14 — Real-Time Notifications, Accessibility & Localization

Weeks 28–29

Sprint Goal:  Cross-cutting polish pass across all three portals.

Key User Stories / Backlog Items

- Real-time notification service: weather alerts, travel advisories, booking reminders/countdown, companion-activity notifications.

- Urdu localization pass (Noto Nastaliq Urdu, full RTL rendering) across the key customer flows.

- Accessibility audit to WCAG 2.1 AA: screen-reader pass on booking/itinerary flows, contrast checks, 44×44px minimum tap targets.

- Performance pass: query optimization and Redis caching on hot endpoints (destination search, home feed, planner retrieval).

Deliverables

- Notification service (WebSocket/push).

- Localization bundle and accessibility audit report.

- Performance benchmark report with before/after metrics.

Definition of Done:  Automated accessibility scan (e.g. axe-core) reports zero critical issues on core flows; Urdu RTL screens are screenshot-verified.

Testing Focus:  Accessibility scanner in CI; localization visual regression; load test comparison pre/post caching changes.

## Sprint 15 — Hardening, Security & QA Regression

Weeks 30–31

Sprint Goal:  Stabilize the full system before launch with a comprehensive regression and security pass.

Key User Stories / Backlog Items

- End-to-end suite (Playwright/Cypress) covering the five key user flows from the UX plan: AI trip planning, institutional student joining a trip, organizer publishing a trip, admin approving an organizer, and parent tracking a child.

- Security review: dependency vulnerability audit, secrets scanning, RBAC penetration pass, rate limiting on auth and AI planner endpoints.

- Load testing on the planner endpoint, GPS sync, and search under concurrent load.

- Structured bug bash across web, mobile, and all three portals; triage and fix regressions.

Deliverables

- E2E suite running in CI on every merge to main.

- Security audit report and load-test report.

- Bug backlog cleared of all P0/P1 issues.

Definition of Done:  CI is green across web, mobile, and backend; zero open critical/high vulnerabilities; load test meets the agreed target (e.g. 200 concurrent planner sessions with acceptable latency).

Testing Focus:  Full regression E2E run; dependency and secrets scanning in CI; load testing with a tool such as k6 or Locust.

## Sprint 16 — Production Deployment & FYP-II Final Demo

Weeks 32–33

Sprint Goal:  Deploy to production and prepare final evaluation materials.

Key User Stories / Backlog Items

- Production deployment: Dockerized backend on Railway/Render, web app on Vercel, managed Postgres/Redis/Qdrant tiers.

- Domain and SSL setup; staged environment-promotion pipeline (staging → production with a manual approval gate).

- Monitoring and alerting: uptime checks, error tracking (e.g. Sentry), centralized log aggregation.

- Final documentation: architecture document, API reference, user manual, and FYP report appendix.

- Final demo rehearsal and FYP-II defense materials.

Deliverables

- Live production system.

- Monitoring dashboards and alert rules.

- Complete documentation set and final presentation deck.

Definition of Done:  Production smoke tests pass; a rollback procedure is documented and has been rehearsed at least once; the FYP-II demo runs successfully end-to-end.

Testing Focus:  Production smoke test suite; rollback rehearsal in staging; final live run-through of all five key user flows.

▶ FYP-II MILESTONE: Final evaluation, live production demo, and project defense.

# 6. Risk Management & Mitigation

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| AI/RAG output quality is inconsistent or hallucinates itinerary details | Medium | High | Build the retrieval evaluation harness early (Sprint 4); ground generation in retrieved facts; always show sources/estimates as approximate. |
| Store-and-forward GPS sync loses or duplicates location data | Medium | High | Incremental sync with a `synced` flag and server-side idempotent stitching; dedicated offline-simulation test suite (Sprint 12). |
| Institutional domain-lock is bypassed (a non-student enrolls) | Low | High | Server-side re-verification at enrollment time, not just at signup; explicit negative test case in CI (Sprint 8). |
| Third-party payment gateway integration (Safepay/JazzCash) slips or has sandbox limitations | Medium | Medium | Start sandbox integration early relative to launch (Sprint 13, with buffer before Sprint 15 hardening); design bookings to degrade gracefully if a gateway is down. |
| Team member availability changes (exams, illness) mid-project | Medium | Medium | Cross-train on critical modules; keep PRs small so any teammate can pick up unfinished work; maintain up-to-date documentation. |
| Mobile offline-first complexity underestimated | Medium | Medium | Dedicated sprint (11) solely for offline architecture before layering GPS tracking on top in Sprint 12. |
| Scope creep beyond the approved UX plan | Medium | Low | All new requests are logged as backlog items and prioritized in sprint planning, not added mid-sprint. |

# 7. Deployment & DevOps Plan

## 7.1 Environments

- Local (Docker Compose) → Staging (auto-deployed on merge to main) → Production (manual approval gate after staging smoke tests).

## 7.2 Infrastructure

- Backend: Dockerized FastAPI services on Railway/Render.

- Web: Vercel, deployed from the same monorepo/pipeline.

- Mobile: signed Android/iOS builds distributed via internal testing tracks during development; store submission considered out of scope for the FYP unless explicitly required.

- Managed PostgreSQL, Redis, and Qdrant instances for staging and production, separate from local dev data.

## 7.3 Monitoring & Observability

- Error tracking (e.g. Sentry) across web, mobile, and backend.

- Centralized log aggregation for the backend.

- Uptime checks on all public endpoints with alerting to the team.

## 7.4 Rollback Strategy

- Every production deploy is tied to a specific tagged release; rollback means redeploying the previous tag plus, if needed, a reverse database migration.

- Database migrations are written to be reversible wherever practical, and destructive migrations are always preceded by a backup step.

# 8. Quality Assurance Strategy Summary

| Layer | Tooling | Owner | Cadence |
| --- | --- | --- | --- |
| Static analysis / lint | Ruff, mypy, ESLint, flutter_lints | Every engineer, on every PR | Continuous (CI) |
| Unit tests | Pytest, Flutter test | Feature owner | Every PR |
| Integration tests | Pytest against dockerized Postgres/Redis/Qdrant | Backend engineer(s) | Every PR touching backend |
| End-to-end tests | Playwright / Cypress | Whole team | Nightly in CI from Sprint 6; full suite from Sprint 15 |
| Accessibility | axe-core, manual screen-reader pass | Web/mobile frontend engineers | Sprint 14, then spot-checked each sprint |
| Security | Dependency audit, secrets scanning, RBAC pass | Whole team | Continuous (CI) + dedicated pass in Sprint 15 |
| Load testing | k6 or Locust | Backend engineer(s) | Sprint 15, repeated before production launch |

# 9. Appendix

## 9.1 Definition of Done — Full Checklist

- Feature matches the corresponding wireframe/UX plan section, or a documented, agreed deviation exists.

- Code merged via a reviewed pull request with green CI.

- Automated tests written and passing (unit + integration where applicable).

- No new critical/high static-analysis or dependency-vulnerability findings.

- API changes reflected in the OpenAPI spec and Postman collection.

- Manual QA performed against the sprint's acceptance criteria before the sprint review.

- Relevant documentation (README/ADR) updated.

- Deployed to staging and verified there before being marked done.

## 9.2 UX Plan → Sprint Traceability

| UX Plan Section | Delivered In |
| --- | --- |
| 2. Authentication & Onboarding | Sprint 1, Sprint 2 |
| 3.1–3.3 Home, AI Planner, Discovery | Sprint 2, Sprint 3, Sprint 5 |
| 3.4 Itinerary Management | Sprint 6 |
| 3.5 Booking & Payments | Sprint 13 |
| 3.6 Offline Mode & Store-and-Forward GPS | Sprint 11, Sprint 12 |
| 3.7 Organizer-Published Itineraries | Sprint 7, Sprint 8 |
| 3.8 Real-Time Updates & Notifications | Sprint 14 |
| 4. Organizer Portal | Sprint 7, Sprint 13 (analytics) |
| 5. Admin Console | Sprint 8, Sprint 9 |
| 6. Design System Guidelines | Sprint 2, Sprint 14 (accessibility/localization) |
| 8. Technical UX Considerations | Sprint 4 (RAG), Sprint 11–12 (offline/GPS), Sprint 8 (domain verification) |

Rah-e-Ravaan Development Plan  ·  BSCS FYP  ·  Confidential Draft